## Server Build Sheet
Sl No | Build Date: 28-08-2024
1 | Parent RITM | Child RITM | RITM Transition | VM Name | IP Address | Cluster |  | VCenter | Date | Status
2 | RITM4915753(Win Build) | RITM4925517 | RITM4935838 | WBGVSIMATICP001 | 10.6.64.55 | BGHADRS001 |  | WB5VC001 | 2024-08-28 | Completed
3 | RITM4926384(Linux Build)
4
5 | Build Date: 02-09-2024 | (Windows Build)
6 | DC | vCPU | vRAM | Storage | Parent RITM | Child Build RITM | Trasition RITM | CTASK | Project Name/Server Description | Hostname | C | D | Page | OS | Build Engineer | Build N/W | Status
7 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939377 | RITM4944198 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922072 | W6OVSNATMP001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
8 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939380 | RITM4944227 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922075 | W6OVSNATMP002 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
9 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939376 | RITM4944242 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922081 | W6OVSNATMS001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
10 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939374 | RITM4944249 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922086 | W6OVSNATMD001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
11
12 | Build Date: 02-09-2024 | (Linux Build)
13 | DC | vCPU | vRAM | Storage | IP Address | Cluster | Parent RITM | Child RITM | Transition RITM | project Name/Server Description | CTASK | Hosname | C | D | Page | OS | Build Engineer | N/W | Status
14 | 0B-GDC | 4 | 16 | 300 | 172.17.37.71 | 0BUAPPPRD001 | RITM4935184 | RITM4940342 | RITM4949251 | STOR management server | TASK0326044 | u0bvstormp01 | 120 | NA | 32 | RHEL 9.2 | Keshavamurti KV | Ent | Completed
15
16 | Build Date: 03-09-2024 | (Win22k Build)
17 | DC | vCPU | vRAM | Storage | Parent RITM | Child RITM | Trasition RITM | Project Name/Server Description | Hostname | C | D | E | T | L | Pagedrive | Sign Date | IP Address | OS | Build Engineer | Build N/W | Status
18 | 23-BRISBANE | 4 | 16 | 352 | RITM4913807 | RITM4947723 |  | KTLO - APAC - OSD/API Adhoc Requests-Carole Park Site 23 - BMS server build for DesigoCC-SVCRITM4913800 | W23VDCCBMSD001 | 120 | 100 | 100 | 0 | 0 | 32 | 2024-09-03 | 10.6.49.247 | W2k22 | Keshavamurti KV | MFG | Closed
19 | 23-BRISBANE | 4 | 16 | 402 | RITM4913807 | RITM4947724 |  | KTLO - APAC - OSD/API Adhoc Requests-Carole Park Site 23 - BMS server build for DesigoCC-SVCRITM4913795 | W23VDCBMSDBD001 | 120 | 100 | 100 | 25 | 25 | 32 | 2024-09-03 | 10.6.49.248 | W2k22 | Keshavamurti KV | MFG | Closed
20
21 | Manual Build Windows 2k19 | 2024-09-11
22 | Cluster | DC | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Build Verification task | Project Name/Server Description | OS | Hostname | C Drive | D Drive | Pagedrive | VLAN | IP Address | N/W | CI Creation RITM | Priv acc | autologoff | Ci Relationship | Firewall Port Open | Change Request | Status
23 | E7HADRS001 | E7-DAL | 4 | 16 | 252 | RITM4936056 | RITM4957831 | RITM4978786 | TASK0328641 | MES EIH server - E7 | WE2K19 STD | WE7VMESEIHP001 | 120 | 100 | 32 | E7-DVPG-PC-MES-1126 | 10.4.37.106 | MFG Build | RITM4963040 | RITM4964353 | RITM4964366 | RITM4964392 | RITM4963222 | CHG0169182 | Closed
24
25 | Manual Build Windows 2k22 | 2024-09-12
26 | Cluster | DC | vCPU | vRAM | Storage | RITM/Project ID | Child RITM | Transition RITM | Project Name/Server Description | OS | Hostname | C Drive | D Drive | E Drive | T_TempDrive | L_LogDrive | Additional Drive | Pagedrive | VLAN | IP Address | SQL | Build Engineer | Build N/W | Status
27 | 5DHADRS003 | 5D-HUNGARY | 4 | 16 | 252 | RITM4942756 | RITM4964150 | RITM4969410 | Komarom - NexOn System Upgrade -App | W2K22 STD | W5DVNEXAPPP001 | 120 | 100 |  |  |  |  | 32 | 152 | 10.248.201.7 |  | Keshavamurti KV | ENT | Closed
28 | 5DHADRS003 | 5D-HUNGARY | 4 | 16 | 584 | RITM4942756 | RITM4964149 | RITM4969420 | Komarom - NexOn System Upgrade -DB | W2K22 STD | W5DVNEXDBP001 | 120 | 100 | 200 | 50 | 50 |  | 32 | 154 | 10.248.203.7 | SQL19 STD | Keshavamurti KV | ENT | Closed
29
30 | Automation Build ENT N/W | 19-09-2024-24-09-2024 | DM-Sreeraj p | CI/Handover Owner:Ravishankar Sethuraman
| DC | Cluster | Vcenter | vCPU | vRAM | Storage | RITM | Child RITM/CI Owner | Build Verification | Trasition RITM | Project Name/Server Description | Hostname | IP Address | OS | C Drive | D Drive | Add | Page | Build Engineer | Status
31 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973722 | TASK0330635 | RITM4978170 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2--SVCRITM4915920 | W0BVTWS008 | 172.17.36.174 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
32 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973730 | TASK0330635 | RITM4978186 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915934 | W0BVTWS009 | 172.17.36.177 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
33 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973727 | TASK0330635 | RITM4978191 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915944 | W0BVTWRPTS003 | 172.17.36.178 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
34 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973729 | TASK0330635 | RITM4978195 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915961 | W0BVTWD001 | 172.17.36.183 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
35 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973723 | TASK0330635 | RITM4978197 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915973 | W0BVTWD002 | 172.17.36.184 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
36 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973720 | TASK0330635 | RITM4978199 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915982 | W0BVTWRPTD001 | 172.17.36.187 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
37
38 | Automatio MFG Buiid 25-10-2024 | DM-Sreeraj p
39 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Build Verification Task | Trasition RITM | Project Name/Server Description | Hostname | C Drive | D Drive | Page | IP Address | OS | Build Engineer | Status
40 | 6J-AURANGABAD | 6JHADRS003 | w6evc001 | 4 | 16 | 252 | RITM4920471 | RITM5031584 | TASK0338730 | RITM5035727 | MES Upgrade for Packaging eBR- New EIH server- SVCRITM4920462 | W6JVMESEIHP002 | 120 | 100 | 32 | 192.168.113.11 | W2K19 | Keshav | Closed
41
42 | New Esxi Builds for C6-DUBLIN projects 05th Nov 2024--Delivered on 18th Nov 2024 DELL R750 Model
43 | [5 empty] | IDRAC Default Creds: root/$3CuredW@ll! Esxi Default Creds: root/20Pme1esx!
44 |  |  |  |  | Closed Change Request
46 | Esxi Hostname | IDRAC IP Address | Esxi IP Address | VMotion IP Address |  | AD DNS TASK | Trasition RITM | Change Request for VM migration Closed
47 | Ec6rr7u02.myl.com | 10.243.94.76 | 10.243.94.79 | 10.243.93.101 | CHG0173549 | CTASK0549124 | RITM5074799 | CHG0174471
48 | Ec6rr7u04.myl.com | 10.243.94.77 | 10.243.94.80 | 10.243.93.102 | CHG0173553 | CTASK0549127 | RITM5074800 | CHG0174471
49 | Ec6rr7u06.myl.com | 10.243.94.78 | 10.243.94.81 | 10.243.93.103 | CHG0173554 | CTASK0549128 | RITM5074801 | CHG0174471
50
51 | Automation Build ENT N/W | 20-11-2024-21-11-2024 | DM-Sreeraj p | CI/Handover Owner:Siva Kumar Tandai
52 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Project Name/Server Description | Hostname | C Drive | D Drive | Page | IP Address | OS | Build Engineer | Status
53 | 07-DR | 07WAPPDR003 | w07vc001 | 4 | 32 | 284 | RITM4924525 | RITM5078980 | RITM5085351 | Global TrackWise - Upgrade 10/11 -10.2 to 10.9 - HA & DR-SVCRITM4924478 | W07VTWP013 | 120 | 100 | 64 | 172.26.145.14 | W2K22 | Keshav | Closed
54 | 07-DR | 07WAPPDR003 | w07vc001 | 4 | 32 | 284 | RITM4924525 | RITM5078974 | RITM5085354 | Global TrackWise - Upgrade 10/11 -10.2 to 10.9 - HA & DR-SVCRITM4924484 | W07VTWP014 | 120 | 100 | 64 | 172.26.145.15 | W2K22 | Keshav | Closed
55 | 07-DR | 07WAPPDR003 | w07vc001 | 4 | 32 | 284 | RITM4924525 | RITM5078972 | RITM5085355 | Global TrackWise - Upgrade 10/11 -10.2 to 10.9 - HA & DR-SVCRITM4924489 | W07VTWP015 | 120 | 100 | 64 | 172.26.145.153 | W2K22 | Keshav | Closed
56
57 | Automation Build MFG N/W | 22-11-2024-26-11-2024 | DM-Sreeraj p | CI/Handover Owner:Vibha Vallabh Env: QA server
58 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Project Name/Server Description | Hostname | C Drive | D Drive | N/A | N/A | N/A | Page | IP Address | OS | Build Engineer | Status
59 | 6O-IDC | 6OWAPPNPRD001 | 6ovcsa002 | 4 | 16 | 252 | RITM4915458 | RITM5054174 | RITM5088562 | Global - MES Core 3.0 (PharmaSuite 11.1 for MYMES Core Environment- SVCRITM4915420 | W6OVMESQ002 | 120 | 100 | 0 | 0 | 0 | 32 | 10.232.46.105 | W2K19 | Keshav | Closed
60 | 6O-IDC | 6OWAPPNPRD001 | 6ovcsa002 | 4 | 16 | 252 | RITM4915458 | RITM5054172 | RITM5088563 | Global - MES Core 3.0 (PharmaSuite 11.1 for MYMES Core Environment- SVCRITM4915438 | W6OVMESQ003 | 120 | 100 | 0 | 0 | 0 | 32 | 10.232.46.106 | W2K19 | Keshav | Closed
61
62 | Automation Build MFG N/W | 26-11-2024-29-11-2024 | DM-Meghashyam K | CI/Handover Owner:Ashutosh V Parab
63 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Build Verification | Project Name/Server Description | Hostname | C Drive | D Drive | N/A | N/A | N/A | N/A | Page | IP Address | OS | Build Engineer | Status | Description
64 | 6T-INDORE | 6TWAPPPRD002 | w6evc001 | 8 | 32 | 544 | RITM4781610 | RITM5028712 | RITM5094803 | TASK0338068 | Multi-Site – Data Historian Rollouts VDH implementation- SVCRITM4781572 | W6TVGDINPIOD001 | 120 | 120 | 120 |  | 120 | 0 | 64 | 10.6.32.66 | W2K19 | Keshav | Closed | Interface Node - Pi & OPC - Dev- Indore
65 | 6T-INDORE | 6TWAPPPRD002 | w6evc001 | 8 | 32 | 684 | RITM4781610 | RITM5028711 | RITM5094804 | TASK0338068 | Multi-Site – Data Historian Rollouts VDH implementation- SVCRITM4781586 | W6TVGDINPIOP002 | 120 | 250 | 250 |  |  | 0 | 64 | 10.6.32.68 | W2K19 | Keshav | Closed | Interface Node 2 - Pi & OPC - Production - Indore
66 | 6T-INDORE | 6TWAPPPRD002 | w6evc001 | 8 | 32 | 1404 | RITM4781610 | RITM5028713 | RITM5094806 | TASK0338068 | Multi-Site – Data Historian Rollouts VDH implementation- SVCRITM4781588 | W6TVGDSHFTP001 | 120 | 120 |  |  |  | 1100 | 64 | 10.6.32.69 | W2K19 | Keshav | Closed | FT Historian Server -Indore
68
69 | Automation Build ENT N/W | 28-11-2024-30-11-2024 | DM-Meghashyam K | CI/Handover Owner:Viral Shah
70 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | CTASK | Project Name/Server Description | Hostname | C Drive | D Drive | Page | IP Address | OS | Build Engineer | Status
71 | 6J-AURANGABAD | 6JHADRS003 | w6evc001 | 4 | 16 | 302 | RITM5091816 | RITM5094383 | RITM5096559-Pending | TASK0345982 | KTLO - APAC - OSD/API Adhoc-Server for Canon Uniflow-SVCRITM5091815 | W6JVUNIFLOWP003 | 120 | 150 | 32 | 172.28.177.103 | W2K22 | Keshav | Closed
72
73 | Automation Build MFG N/W | 12-01-2025 15-01-2025 | DM-Ajay Kumar | CI/Handover Owner:Neema Bisht
74 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | CTASK | Hostname | C Drive | D Drive |  | Page | IP Address | OS | Build Engineer | Status
75 | 1L-SanAntonioMFG | 1LWAPPPRD001 | w0bvc001 | 4 | 16 | 352 | RITM4943029 | RITM5167003 |  | SRA for Manufacturing Systems Implementation Device-SVCRITM4943012 | W1LVSRAPSMP001 | 120 | 200 | 0 | 32 | 192.168.224.20 | W2K22 | Keshav | Closed
76
77 | Manually SRA Build Server(0B&07) | OS-Win 2K22
78 | Hostname | Change Request | Transition RITM
79 | W0BPVSRAP001 | CHG0175768
80 | W0BPVSRAP002 | CHG0175774
81 | W07PVSRADR001 | CHG0175777
82
73 | Automation Build MFG N/W | 11-03-2025 19-03-2025 | DM-Shital Nitin Neralkar | CI/Handover Owner:
74 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | CTASK | Hostname | C Drive | D Drive |  | Page | IP Address | OS | Build Engineer | Status
85 | wb5vc001 | 5DHADRS001 | wb5vc001 | 4 | 8 | 236 | RITM5251621 | RITM5273078 | RITM5289947 | TASK0368508 | W5DVADC002 |  |  |  |  | 10.6.176.141 | W2K19 | Keshav | Closed
86 | wb5vc001 | 5DHADRS001 | wb5vc001 | 4 | 8 | 236 |  | RITM5273076 | RITM5289946 | TASK0368508 | W5DVPRTP002 |  |  |  |  | 10.6.176.143 | W2K22 | Keshav | Closed
86 | wb5vc001 | 5DHADRS001 | wb5vc001 | 8 | 32 | 494 |  | RITM5273077 | RITM5289945 | TASK0368508 | W5DSECP002 |  |  |  |  | 10.6.176.142 | W2K22 | Keshav | Closed
88
89 | Automation Build MFG N/W | 25-03-2025 04-04-2025 | DM-Meghashyam K | CI/Handover Owner:
90 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | CTASK | Hostname | C Drive | D Drive |  | Page | IP Address | OS | Build Engineer | Status
91 | 23-sa40210.myl.com | 23MHADRS001 | 23-sa40210.myl.com | 8 | 32 | 784 | RITM5254919 | RITM5286688 |  | TASK0370119 | W23VIDAAPP002 |  |  |  |  | 10.4.232.24 | Microsoft Windows Server 2019 | Keshav | Closed
92
93 | Automation Build ENT N/W | 22-05-2025-23-05-2025 | DM-Ajay Kumar | CI/Handover Owner:Vijay Khamat
94 | DC | Cluster | Vcenter | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | CTASK | Project Name/Server Description | Hostname | C Drive | D Drive | Page | IP Address | OS | Build Engineer | Status
95 | wb5vc001 | 5HHADRS001 | wb5vc001 |  |  |  | RITM5392192 | RITM5397565 | RITM5405499 | [7 empty] | Windows server 2022 | Keshav | Closed
96
104 | Transition RITM
105 | RITM5294469
106 | RITM5294580
115 | ENT Builds | [6 empty] | Transition
116 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423873 | WIP | TASK0386479 | 0B-GDC | W0BVHYPHFMP001 | RITM5431411 | 16 | 96 | 484 | Prod | 2025-06-12 |  | Keshav | N/A | ATM | WIP
117 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423884 | WIP | TASK0386479 | 0B-GDC | W0BVHYPHFMP002 | RITM5431412 | 16 | 96 | 484 | Prod | 2025-06-12 |  | Keshav | N/A | ATM | WIP
118 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423868 | WIP | TASK0386479 | 0B-GDC | W0BVHYPREPP001 | RITM5431414 | 8 | 32 | 484 | Prod | 2025-06-12 |  | Keshav | N/A | ATM | WIP
119 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423887 | WIP | TASK0386479 | 0B-GDC | W0BVHYPREPP002 | RITM5431415 | 8 | 32 | 484 | Prod | 2025-06-12 |  | Keshav | N/A | ATM | WIP
120 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423865 | WIP | TASK0386479 | 0B-GDC | W0BVHYPDRMP001 | RITM5431416 | 4 | 16 | 452 | Prod | 2025-06-12 |  | Keshav | N/A | ATM | WIP
121 | 0B-GDC Site ENT Builds
122 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423873 | Closed | TASK0386479 | 0B-GDC | W0BVHYPHFMP001 | V | 16 | 96 | 484 | Prod | 2025-06-12 | 2025-06-06 | Keshav | N/A | ATM | Closed | Tran-RITM5431411
123 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423884 | Closed | TASK0386479 | 0B-GDC | W0BVHYPHFMP002 | V | 16 | 96 | 484 | Prod | 2025-06-12 | 2025-06-06 | Keshav | N/A | ATM | Closed | Tran-RITM5431412
124 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423868 | Closed | TASK0386479 | 0B-GDC | W0BVHYPREPP001 | V | 8 | 32 | 484 | Prod | 2025-06-12 | 2025-06-06 | Keshav | N/A | ATM | Closed | Tran-RITM5431414
125 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423887 | Closed | TASK0386479 | 0B-GDC | W0BVHYPREPP002 | V | 8 | 32 | 484 | Prod | 2025-06-12 | 2025-06-06 | Keshav | N/A | ATM | Closed | Tran-RITM5431415
126 | EPM 2024-2025 Upgrade | RITM5394649 | RITM5423865 | Closed | TASK0386479 | 0B-GDC | W0BVHYPDRMP001 | V | 4 | 16 | 452 | Prod | 2025-06-12 | 2025-06-06 | Keshav | N/A | ATM | Closed | Tran-RITM5431416
127
128 | 0B-GDC Site ENT Builds | [6 empty] | Transition
129 | Multi-Site - Cleaning Validation Software Implementation | RITM5395405 | RITM5423854 | WIP | TASK0386473 | 0B-GDC | C0BVCVMCTXP005 | RITM5445670 | 8 | 64 | 384 | Prod | 2025-06-13 |  | Keshav | N/A | ATM | WIP
130 | Multi-Site - Cleaning Validation Software Implementation | RITM5395405 | RITM5423844 | WIP | TASK0386473 | 0B-GDC | C0BVCVMCTXP006 | RITM5445671 | 8 | 64 | 384 | Prod | 2025-06-13 |  | Keshav | N/A | ATM | WIP
131 | Multi-Site - Cleaning Validation Software Implementation | RITM5395405 | RITM5423846 | WIP | TASK0386473 | 0B-GDC | C0BVCVMSDBD001 | RITM5445673 | 8 | 32 | 834 | Dev | 2025-06-13 |  | Keshav | N/A | ATM | WIP
132 | Multi-Site - Cleaning Validation Software Implementation | RITM5395405 | RITM5423853 | WIP | TASK0386473 | 0B-GDC | C0BVCVMSDBT001 | RITM5445674 | 8 | 32 | 834 | Test | 2025-06-13 |  | Keshav | N/A | ATM | WIP
133 | Multi-Site - Cleaning Validation Software Implementation | RITM5395405 | RITM5423847 | WIP | TASK0386473 | 0B-GDC | C0BVCVMSDBP001 | RITM5445677 | 16 | 64 | 1920 | Prod | 2025-06-13 |  | Keshav | N/A | ATM | WIP
134 | 6B-NASHIK MFG Builds
135 | RITM5446060 | 6B-NASHIK | W6BVIDBSDBP001 | 192.168.141.49 | Keshav
136 | RITM5446065 | 6B-NASHIK | W6BVIDAAPPP001 | 192.168.141.50 | Keshav
137 | RITM5446063 | 6B-NASHIK | W6BVIDAAPPP002 | 192.168.141.51 | Keshav
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314

## Server Upgrade Sheet
Sl No | RITM4930961 - D2 - Scale up and Extend Usage for Additional Doc Types & Sites | 2024-09-16
1 | Hostname | Vcenter | Child RITM | Current Version | Target Version | Change Request
2 | W0BD216MIGD004 | w0bvc001 | RITM4958581 | 2016 | 2022 | CHG0169373
3 | W0BD216MIGD005 | w0bvc001 | RITM4958583 | 2016 | 2022 | CHG0169374
4 | W0BD216MIGD006 | w0bvc001 | RITM4958576 | 2016 | 2022 | CHG0169375
5 | w6vagiacltp001 | w6vvc001 | RITM4958572 | 2012 | 2022 | CHG0169383/CHG0169384
6
7 | W0BD216MIGD004 | CHG0169373 | 18-Sep-24(06 AM to 06 PM) | Completed
8 | W0BD216MIGD005 | CHG0169374
9 | W0BD216MIGD006 | CHG0169375
10 | W6VAGIACLTP001(w6vvc001.myl.com) | CHG0169383 | 2012-2019 | Completed | yet to start | Manually Upgrade
11 |  | CHG0169384 | 2019-2022
12
13 | 25-09-2024(10 AM - 10 PM)
14 | Parent RITM | Child RITM | RE: Intake ID - RITM4781454 - Mylan Canada Quality Control Lab Inventory Tracking Application 4 Server Builds -Signed off | Delivery Mgr: Meghashyam K M | Request Owner: Steve Lough, Abdul Shameem | OS-Version | Service Name
15 | RITM4918868 | RITM4966725 | W15myp001 | CHG0170100-Closed | I have been through all of the processes and performed a release to the server and everything is working.¦ Steve | 2019-2022 | Application Servers
16 | RITM4918868 | RITM4966731 | W15myp002 | CHG0170104-Closed |  | 2019-2022
17 | RITM4918868 | RITM4966733 | W15myp003 | CHG0170106-Closed |  | 2016-2022
18 | RITM4918868 | RITM4966728 | W0bmypwd001 | CHG0170101-Closed |  | 2016-2022
19 | RITM4922480 | RITM4969714 | w0bmypdbd001 | CHG0170102-Closed | Completed | 2016-2022 | DB Server
20
21 | 26-09-2024(10 AM- 10 PM)
22 | Parent RITM | Child RITM | D2 Dev Migration Servers OS upgrade | Delivery Mgr: Meghashyam K M | Request Owner: Janardhan Madhavarapu | OS-Version | Service Name
23 | RITM4930961 | RITM4958569 | W0BD216MIGD002 | CHG0170346 | Server and applications are running fine. Thanks and Regards, Komal Madan | 2016-2022 | Application Servers
24 | RITM4930961 | RITM4958567 | W0BD216MIGD007 | CHG0170350 |  | 2016-2022
25 | RITM4930961 | RITM4958565 | W0BD216MIGD008 | CHG0170351 |  | 2016-2022
26 | RITM4930961 | RITM4958584 | W0BD216MIGD009 | CHG0170352 |  | 2016-2022
27
32 | Intake on 04-Oct-2024 | DM: Meghashyam M | D2 Dev Migration Servers OS upgrade ¦ Activity Scheduled on 09th Oct 2024 10AM-10PM ¦ Requestor: Janardhan Madhavarapu |  |  | Environment
33 | Parent RITM | Child RITM | Hostname | Change Requests | Current version | Testing Servers
34 | RITM4930961 | RITM4958563 | W0BD216MIGT004 | CHG0171045 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | CHG0168951-OS Upgrade.. reference change.
35 | RITM4930961 | RITM4958571 | W0BD216MIGT005 | CHG0171046 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | For the OS Upgrade Task Steps:
36 | RITM4930961 | RITM4958560 | W0BD216MIGT006 | CHG0171047 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Open the Service Catalog.
37 | RITM4930961 | RITM4958575 | W0BD216MIGT007 | CHG0171048 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Select OS In-Place Upgrade (Windows).
38 | RITM4930961 | RITM4958561 | W0BD216MIGT008 | CHG0171049 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Fill in the required details: Vcenter name, Hostname, Downtime, ISO path, and OS name.
39 | RITM4930961 | RITM4958570 | W0BD216MIGT009 | CHG0171050 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Submit the request; this will generate an RITM with a Change Request number.
40 | [7 empty] | Please forward the RITM to the technical approver (Venu).Put the server in maintainance mood manually by maintainance schedules.
41 | Intake on 14-Oct-2024 | DM: Meghashyam M | D2 Dev Migration Servers OS upgrade ¦ Activity Scheduled on 17th Oct 2024 10AM-10PM ¦ Requestor: Janardhan Madhavarapu |  |  | Environment |  | For the OS Upgrade Task Steps:
42 | Parent RITM | Child RITM | Hostname | Change Requests | Current version |  |  | First, check the available space on the C drive; ensure there is a minimum of 35GB.
43 | RITM4930961 | RITM4958578 | W0BD216MIGD001 | CHG0171655 | Microsoft Windows Server 2016 STD- 2022 STD | Dev |  | If there is insufficient space, clear any unwanted files.
44 | RITM4930961 | RITM4958577 | W0BD216MIGD003 | CHG0171659 | Microsoft Windows Server 2016 STD- 2022 STD | Dev |  | Monitor the C request. Close the App and DB service tasks; snapshots will be taken care of automatically.
45 | RITM4930961 | RITM4958582 | W0BD216MIGT001 | CHG0171658 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Mount the ISO to the VM and start the upgrade process.(Automatically)
46 | RITM4930961 | RITM4958566 | W0BD216MIGT002 | CHG0171656 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Monitor the status in the VM through the LogView folder using Script1.
47 | RITM4930961 | RITM4958564 | W0BD216MIGT003 | CHG0171657 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Need to monitor the Change Request and Reuest Pending Change RITM's
48 | [7 empty] | Close the App and DB service CTasks.
49 | Intake on 05-Nov-2024 | DM: Shital N | RITM5083480- SAP_ End of Support Life (EOSL) W0BRTMP001 OS Upgrade ¦ Activity Scheduled on 16th Dec 2024 06.30 AM-2PM ¦ Requestor: Nisha Bhat
50 | Parent RITM | Child RITM | Hostname | Change Requests | Current version | Environment |  | Inform the server owner to start the application services and check the status.
51 | RITM5083480 | RITM5099388 | w0brtmp001 | CHG0176747 | Microsoft Windows Server 2012 R2 STD- 2022 STD | Jump Server |  | Attach the post-upgrade activity details, including: 1. Hostname and Properties, 2. Drive Details, 3. Screenshot
52 | [7 empty] | 1. Upgrade the VMware Tools.
53 | Hostname | OS | CTASK |  |  |  |  | 2. Change the hardware compatibility version to the latest version.
54 | w0brtmp001 | Microsoft Windows Server 2019 STD | CTASK0558062 |  |  |  |  | 3. Update the Guest OS version in the VMware Options console (OS Container).
55 | [7 empty] | 4. Inform the Patch team to push the latest updates.
56 | [7 empty] | 5. Uninstall the Carbon Black Agent from the old servers 2022 servers no need this agent.
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370

## C6-DUBLIN-Migration
Sl No
1 | C6 Cluster Migration Plan | DM: Senthinathan J
2 | C6HADRS003---> 001 &002 All VM's need to migrate from cluster 3 to 2&1 | [5 empty] | C6-DUBLIN Location DELL Serevers
3 | and need to add all cluster 3 nodes to cluster 2 | [5 empty] | Sl.No | Make & Model | Serial Number | Hostname | IP Address | Remarks/Status
4 | [6 empty] | 1 | DELL PowerEdge R740 | F31SYP3 | ec6rr0u11.myl.com | 10.243.94.15 | Done
5 | C6-DUBLIN(4 Ports, 2MFG, 2ENT, 2FC) | Status/Remarks | Server IP |  |  |  | 2 | DELL PowerEdge R740 | G31SYP3 | ec6rr0u13.myl.com | 10.243.94.16 | Done
6 | C6HADRS001 | Only Cisco Servers | IDRAC IP's |  |  |  | 3 | DELL PowerEdge R740 | H31SYP3 | ec6rr0u15.myl.com | 10.243.94.17 | Done
7 | ec6vm001.myl.com | IMM not reachable | 10.243.94.119 |  |  |  | 4 | DELL PowerEdge R740 | J31SYP3 | ec6rr0u17.myl.com | 10.243.94.18 | Done
8 | ec6vm002.myl.com | IMM not reachable | 10.243.94.118 |  |  |  | 5 | DELL PowerEdge R740 | 141SYP3 | ec6rr0u19.myl.com | 10.243.94.19 | Done
9 | ec6vm003.myl.com | UP & Reachable | 10.243.94.99 |  |  |  | 6 | CISCO UCS C240 M5S | WZP22351B6D | ec6vm001.myl.com | 10.243.94.116 | Done
10 | ec6vm004.myl.com | IMM not reachable | 10.243.94.98 | Change for Boot Lun Migration: CHG0176742 |  |  | 7 | CISCO UCS C240 M5S | WZP22351B6S | ec6vm002.myl.com | 10.243.94.115 | Done
11 |  |  |  | root |  |  | 8 | CISCO UCS C240 M5S | WZP234215Z3 | ec6vm003.myl.com | 10.243.94.100 | Done
12 | C6HADRS002 | Status/Remarks | Only DELL servers IP | $3CuredW@ll! |  |  | 9 | CISCO UCS C240 M5S | WZP234215YY | ec6vm004.myl.com | 10.243.94.102 | Done
13 | ec6rr0u11.myl.com | IDRAC UP & Reachable | 10.243.94.15 | Esxi Default Creds: root/
14 | ec6rr0u13.myl.com | IDRAC UP & Reachable | 10.243.94.16 | 20Pme1esx!/20pme1esx!/20pme1esx
15 | ec6rr0u15.myl.com | IDRAC UP & Reachable | 10.243.94.17 |  |  |  |  | sc6sansw003# show switchname serialnum
16 | ec6rr0u17.myl.com | IDRAC UP & Reachable | 10.243.94.18 |  |  |  |  | sc6sansw003
17 | ec6rr0u19.myl.com | IDRAC UP & Reachable | 10.243.94.19 |  |  |  |  | Serial Number #1 : JPG232400R2
18 |  |  |  | Vlan : 2010 |  |  |  | Serial Number #2 : JAE23240SZM
19 | C6HADRS003 | Status/Remarks |  | IP : 10.243.93.111 - 115
20 | ec6rr7u02.myl.com | IDRAC UP & Reachable |  | SM : 255.255.255.224
21 | ec6rr7u04.myl.com | IDRAC UP & Reachable |  | DG : 10.243.93.97
22 | ec6rr7u06.myl.com | IDRAC UP & Reachable | [5 empty] | sc6sansw004# show switchname serialnum
23 | [7 empty] | sc6sansw004
Serial Number #1 : JPG252800DH
Sl.No | Hostname | IDRAC IP Address | WWPN1 | WWPN2 |  |  |  | Serial Number #2 : JAE25280FHY
1 | ec6vm001.myl.com | 10.243.94.119 | 20:00:00:B7:71:AD:CA:1C | 20:00:00:B7:71:FF:8E:A4 |  |  |  | sc6sansw004#
2 | ec6vm002.myl.com | 10.243.94.118 | IMM not reachable
3 | ec6vm003.myl.com | 10.243.94.99 | UP & Reachable
4 | ec6vm004.myl.com | 10.243.94.98 | IMM not reachable
5 | ec6rr0u11.myl.com | 10.243.94.10 | 21:00:F4:C7:AA:08:05:6D | 21:00:F4:C7:AA:08:04:CD
6 | ec6rr0u13.myl.com | 10.243.94.11 | 21:00:F4:C7:AA:08:06:07 | 21:00:F4:C7:AA:08:04:D7
7 | ec6rr0u15.myl.com | 10.243.94.12 | 21:00:F4:C7:AA:08:05:6F | 21:00:F4:C7:AA:08:05:0B
8 | ec6rr0u17.myl.com | 10.243.94.13 | 21:00:F4:C7:AA:08:04:E1 | 21:00:F4:C7:AA:08:05:2D
9 | ec6rr0u19.myl.com | 10.243.94.14 | 21:00:F4:C7:AA:08:04:D3 | 21:00:F4:C7:AA:08:05:0F
Sl.No | Hostname | WWPN1 | WWPN2 |  | Sl.No | Make & Model | Serial Number | Hostname | IDRAC IP Address | ESXI IP Address | Remarks/Status
1 | ec6rr0u11.myl.com | 21:00:F4:C7:AA:08:05:6D | 21:00:F4:C7:AA:08:04:CD |  | 1 | CISCO UCS C240 M5S | WZP22351B6D | EC6VM001-IMM | 10.243.94.119 | 10.243.94.116
2 | ec6rr0u13.myl.com | 21:00:F4:C7:AA:08:06:07 | 21:00:F4:C7:AA:08:04:D7 |  | 2 | CISCO UCS C240 M5S | WZP22351B6S | EC6VM002-IMM | 10.243.94.118 | 10.243.94.115
3 | ec6rr0u15.myl.com | 21:00:F4:C7:AA:08:05:6F | 21:00:F4:C7:AA:08:05:0B |  | 3 | CISCO UCS C240 M5S | WZP234215Z3 | EC6VM003-IMM | 10.243.94.99 | 10.243.94.100
4 | ec6rr0u17.myl.com | 21:00:F4:C7:AA:08:04:E1 | 21:00:F4:C7:AA:08:05:2D |  | 4 | CISCO UCS C240 M5S | WZP234215YY | EC6VM004-IMM | 10.243.94.98 | 10.243.94.102
5 | ec6rr0u19.myl.com | 21:00:F4:C7:AA:08:04:D3 | 21:00:F4:C7:AA:08:05:0F |  |  |  |  | Hostname | ESXI IP Address
[8 empty] | EC6VM001.MYL.COM | 10.243.94.116
[8 empty] | EC6VM002.MYL.COM | 10.243.94.115
[8 empty] | EC6VM003.MYL.COM | 10.243.94.100
[8 empty] | EC6VM004.MYL.COM | 10.243.94.102
| Sl.No | Server | MAC Address | MFG/ENT | IP | Port | Host Name
| 1 | ec6rr0u11.myl.com | 78ac.4484.ece4 | [5 empty] | IRE-C6DUB-DIST-SW1
| 2 |  | 78ac.4484.ece5 | [5 empty] | IRE-C6DUB-DIST-SW2
| 3 |  | 6cfe.5464.dcd0 | ENT | 10.243.94.15 | Te1/0/4 | IRE-C6DUB-DIST-SW1
| 4 |  | 6cfe.5464.dcd1 | [5 empty] | IRE-C6DUB-MFG-DIST-SW1
IRE-C6DUB-MFG-DIST-SW2
| 5 | ec6rr0u13.myl.com | 78ac.4484.ece5
| 6 |  | 78ac.4484.ea5d
| 7 |  | 6cfe.5433.0160 | ENT | 10.243.94.16 | Te1/0/5 | IRE-C6DUB-DIST-SW1
| 8 |  | 6cfe.5433.0161
| 9 | ec6rr0u15.myl.com | 78ac.4484.edc4
| 10 |  | 78ac.4484.edc5
| 11 |  | 6cfe.5429.20e0 | ENT | 10.243.94.17 | Te1/0/8 | IRE-C6DUB-DIST-SW1
| 12 |  | 6c:fe:54:29:20:e1
| 13 | ec6rr0u17.myl.com | 78:ac:44:84:e9:94
| 14 |  | 78:ac:44:84:e9:95
| 15 |  | 6c:fe:54:29:0a:00 | ENT | 10.243.94.18 | Te1/0/6 | IRE-C6DUB-DIST-SW1
| 16 |  | 6c:fe:54:29:0a:01
| 17 | ec6rr0u19.myl.com | 78:ac:44:84:e5:3c
| 18 |  | 78:ac:44:84:e5:3d
| 19 |  | 6c:fe:54:24:f9:90 | ENT | 10.243.94.19 | Te1/0/7 | IRE-C6DUB-DIST-SW1
| 20 |  | 6c:fe:54:24:f9:91

## SRA & Trackwise Srvs
Sl.no | Site Code | Location | Make | Model | Qty | Project | OS | Remarks | Priorty | ETA |  | IDRAC IP DETAILS
1 | 0B | GDC, Ashburn | DELL | PE R660 | 1 | SRA | Windows 2022 | On local Harddisk without Domain | 1 | 30th Nov | W0BPVSRAP001-IMM | 172.17.70.18 | 255.255.255.0 | 172.17.70.1
2 | 0B | GDC, Ashburn | DELL | PE R660 | 1 | SRA | Windows 2022 | On local Harddisk without Domain | 2 | 6th Dec | W0BPVSRAP002-IMM | 172.17.70.19 | 255.255.255.0 | 172.17.70.1
| 0'7 | MGW | DELL | PE R660 | 1 | SRA | Windows 2022 | On local Harddisk without Domain | 1 |  |  | 172.31.0.15
3 | 0B | GDC, Ashburn | DELL | PE R750 | 1 | Trackwise | RHEL 8.8 | Sandbox infra, Boot via Storage | 1 | 30th Nov | u0bptwisdbs03-IMM | 172.17.70.164 | 255.255.255.0 | 172.17.70.1
4 | 0B | GDC, Ashburn | DELL | PE R750 | 1 | Trackwise | RHEL 8.8 | Near DR infra, Boot via Storage | 3 | 9th Dec | u0bptwisdbp03-IMM | 172.17.70.165 | 255.255.255.0 | 172.17.70.1
5 | 0B | GDC, Ashburn | DELL | PE R750 | 1 | Trackwise | RHEL 8.8 | PROD Infra, Boot via Stroage | 3 | 9th Dec | u0bptwisdbn03-IMM | 172.17.70.166 | 255.255.255.0 | 172.17.70.1
1 | 0'7 | MGW | DELL | PE R660 | 1 | SRA | Windows 2022 | On local Harddisk without Domain
2 | 0'7 | MGW | DELL | PE R750 | 1 | Trackwise | RHEL 8.8 | DR, Boot via Storage | 2 | 6th Dec | u07ptwisdbf03-IMM | 172.31.0.16 | 255.255.255.128 | 172.31.0.1
IDRAC Creds:
| root |  | Trackwise servers RHEL 8.8
| Vi@tris2024 |  | Boot LUN RITM:RITM5099499
Boot LUN RITM:RITM5099702
1 | u0bptwisdbs03 | fc10/46 500 0x9406a0 10:00:70:b7:e4:21:b8:18 20:00:70:b7:e4:21:b8:18
fc10/46 600 0x1d0900 10:00:70:b7:e4:21:b8:19 20:00:70:b7:e4:21:b8:19
2 | u0bptwisdbp03
3 | u0bptwisdbn03
4 | u07ptwisdbf03

## 5H-Ascendis(SA)
Service Tag | Make & Model | Hostname | IP Address | Subnet | Gateway | Name
HPVSS64 | DELL PowerEdge R760 | u5hpnbmep003 | 172.29.127.137 | 255.255.255.224 | 172.29.127.129 | iDRAC Port
2YVSS64 | DELL PowerEdge R760 | e5hrr2u25.myl.com | 172.29.127.138 | 255.255.255.224 | 172.29.127.129 | iDRAC Port
DPVSS64 | DELL PowerEdge R760 | e5hrr2u23.myl.com | 172.29.127.139 | 255.255.255.224 | 172.29.127.129 | iDRAC Port
6PVSS64 | DELL PowerEdge R760 | e5hrr2u21.myl.com | 172.29.127.140 | 255.255.255.224 | 172.29.127.129 | iDRAC Port
CQVSS64 | DELL PowerEdge R760 | e5hrr2u19.myl.com | 172.29.127.141 | 255.255.255.224 | 172.29.127.129 | iDRAC Port
| Sl.No | Serial Number | N/W DATA Port 1 | N/W DATA Port 1 | FC PORT 1 | FC PORT 2 | Remarks
| 1 | HPVSS64 | PORT 1 UP(Sw 6) | PORT 1 UP(Sw 6) | - | - | -
| 2 | 2YVSS64 | PORT 1 UP(Sw 7 ) | PORT 1 UP(Sw 7) | PORT 1 UP(Sw 7) | PORT 2 UP(Sw 7) | Completed | CHG0180541 - e5hrr2u25
| 3 | DPVSS64 | PORT 1 UP(Sw 8) | PORT 2 UP(Sw 8) | PORT 1 UP(Sw 8) | PORT 2 UP(Sw 8) | Completed | CHG0180537 - e5hrr2u23
| 4 | 6PVSS64 | PORT 1 UP(Sw 9) | PORT 2 UP(Sw 9) | PORT 1 UP(Sw 6) | PORT DOWN(Sw 6) | Completed | CHG0180524 - e5hrr2u21
| 5 | CQVSS64 | PORT 1 UP(Sw 10) | PORT 1 UP(Sw 10) | PORT 1 UP (Sw 21) | PORT DOWN(Sw 21) | Completed | CHG0180519 - e5hrr2u19
[14 empty] | ESXi MGMT |  |  | vMotion IP
| MGMT | Service Tag | Hostname | IP Address | Subnet | Gateway | [7 empty] | IP Address | Subnet | Gateway | IP Address | Subnet | Gateway
| 172.29.127.137-143 | HPVSS64 | u5hpnbmep003 | 172.29.127.137 | 255.255.255.224 | 172.29.127.129 | iDRAC Port | Network SW-1 - S/N:FDO28320JVK | Port ID: Twe1/0/6 | root | $3CuredW@ll! |  | Media | 172.29.127.148 | 255.255.255.224 | 172.29.127.129
| 255.255.255.224 | 2YVSS64 | e5hrr2u25.myl.com | 172.29.127.138 | 255.255.255.224 | 172.29.127.129 | iDRAC Port | Network SW-1 - S/N:FDO28320JVK |  | root | $3CuredW@ll! |  | Server 1 | 172.29.127.149 | 255.255.255.224 | 172.29.127.129 | 172.29.127.162 | 255.255.255.224 | 172.29.127.161
| 172.29.127.129 | DPVSS64 | e5hrr2u23.myl.com | 172.29.127.139 | 255.255.255.224 | 172.29.127.129 | iDRAC Port | Network SW-1 - S/N:FDO28320JVK |  | root | $3CuredW@ll! |  | Server 2 | 172.29.127.150 | 255.255.255.224 | 172.29.127.129 | 172.29.127.163 | 255.255.255.224 | 172.29.127.161
| vMotion | 6PVSS64 | e5hrr2u21.myl.com | 172.29.127.140 | 255.255.255.224 | 172.29.127.129 | iDRAC Port | Network SW-2 - S/N:FDO28320JVP |  | root | $3CuredW@ll! |  | Server 3 | 172.29.127.151 | 255.255.255.224 | 172.29.127.129 | 172.29.127.164 | 255.255.255.224 | 172.29.127.161
| 172.29.127.162-165 | CQVSS64 | e5hrr2u19.myl.com | 172.29.127.141 | 255.255.255.224 | 172.29.127.129 | iDRAC Port |  |  | root | $3CuredW@ll! |  | Server 4 | 172.29.127.152 | 255.255.255.224 | 172.29.127.129 | 172.29.127.165 | 255.255.255.224 | 172.29.127.161
255.255.255.224
| 172.29.127.161 |  | SAN Switches
| NFS | RU | Serial No | Hostname | IP Address | Subnet | Gateway
| 172.29.127.194-197 | 38U | FLM28390BEU | S5HSANSW0012 | 172.29.127.142 | 255.255.255.224 | 172.29.127.129
| 255.255.255.224 | 36U | FLM28390BE8 | S5HSANSW002 | 172.29.127.143 | 255.255.255.224 | 172.29.127.129 |  | Transition RITM
| 172.29.127.193 | [7 empty] | RITM5254470 |  | e5hrr2u25.myl.com | 172.29.127.149
[9 empty] | RITM5254468 |  | e5hrr2u23.myl.com | 172.29.127.150
[9 empty] | RITM5254389 |  | e5hrr2u21.myl.com | 172.29.127.151
[9 empty] | RITM5254386 |  | e5hrr2u19.myl.com | 172.29.127.152
W5HFP001-5H site RDP
S5HSANSW001 & S5HSANSW002
admin
Viatris@123

## 5D-Hungary(Komorom)
| Task Change: CHG0181857 | CHG0182486=VM Migration from MFG 1.0-MFG 2.0 | [8 empty] | parent RITM for 5D-KOM MFG 2.0
Sl.No | wb5vc001.myl.com(5D-HUNGARY) |  | MFG 2 ports need cables to be connected on the server end. | Make & Model | Serial Number | Server Ports |  | Switch Ports |  |  | Automation VM build for 5D-Kom MFG 2.0 | Hostname | IP Address | OS
1 | Cluster | 5DHADRS001 |  |  |  | MFG Port 1 | MFG Port 2 | FOC2431L517 | FOC2431L50Y |  | RITM5273078 | W5DVADC002 | 10.6.176.141 | Microsoft Windows Server 2019
| Esxi Host | e5drr15u18.myl.com | Integrated NIC 1: Intel(R) Ethernet 10G 2P | DELL PowerEdge R750 | BWTDKY3 | Integrated NIC 1 PORT1 | Integrated NIC 1 PORT2 | Te1/0/1 | Te2/0/1 |  | RITM5273077 | W5DVPRTP002 | 10.6.176.143 | Microsoft Windows Server 2022
|  | e5drr15u20.myl.com | Integrated NIC 1: Intel(R) Ethernet 10G 2P | DELL PowerEdge R750 | CWTDKY3 | Integrated NIC 1 PORT1 | Integrated NIC 1 PORT2 | Te1/0/2 | Te2/0/2 |  | RITM5273076 | W5DSECP002 | 10.6.176.142 | Microsoft Windows Server 2022
2 | Cluster | 5DHADRS002 | [8 empty] | RITM5273076
| Esxi Host | e5dr15u10.myl.com | Integrated NIC 1: Intel(R) Ethernet 10G Port 3&4 | DELL PowerEdge R740 | 80YR6J3 | Integrated NIC 1 PORT3 | Integrated NIC 1 PORT4 | Te1/0/3 | Te2/0/4
|  | e5dr15u12.myl.com | Integrated NIC 1: Intel(R) Ethernet 10G Port 3&4 | DELL PowerEdge R740 | 70YR6J3 | Integrated NIC 1 PORT3 | Integrated NIC 1 PORT4 | Te1/0/13 | Te2/0/13 |  | Transition RITM | Hostname | IP Address
5D-KOM Netbackup SRV | [10 empty] | RITM5289947 | W5DVADC002 | 10.6.176.141
IDRAC -> HUN-5DKOM-MFG-DIST-SW1 / 2/0/3 (server side IDRAC port sw side Cisco GLC TE SFP module) | [10 empty] | RITM5289946 | W5DVPRTP002 | 10.6.176.143 | AutoLogoff: RITM5298991
server / NIC1/1 -> HUN-5DKOM-MFG-DIST-SW1 / 1/0/11 (server side Cisco 10G SR sw side Cisco 10G SR SFP module) | [10 empty] | RITM5289945 | W5DSECP002 | 10.6.176.142
server / NIC1/4 -> HUN-5DKOM-MFG-DIST-SW1 / 2/0/11 (server side Cisco 10G SR sw side Cisco 10G SR SFP module) | [10 empty] | Hostname | Make & Model | Serial Number
[11 empty] | e5dr15u10.myl.com | DELL PowerEdge R740 | 80YR6J3
[7 empty] | Switch Ports |  |  |  | e5dr15u12.myl.com | DELL PowerEdge R740 | 70YR6J3
|  |  |  | Hostname | Make & Model | Serial Number | FOC2431L517 | FOC2431L50Y
| DB server migration on 23-05-2025 |  |  | e5drr15u18.myl.com | DELL PowerEdge R750 | BWTDKY3 | Te1/0/1 | Te2/0/1
| W5DVMESDBP001 |  |  | e5drr15u20.myl.com | DELL PowerEdge R750 | CWTDKY3 | Te1/0/2 | Te2/0/2 |  | VLAN NAME | VLAN ID | Subnet | Gateway | Reservation IP
| W5DVMESDBP002 |  |  | e5dr15u10.myl.com | DELL PowerEdge R740 | 80YR6J3 | Te1/0/3 | Te2/0/4 |  | 5D-DVPG-PC-LABSER-1149 | 1149 | 10.6.178.0/27 | 10.6.178.1 | 10.6.178.11 - 10.6.178.20 |  | VLAN's Not available. | 1149 | 10 IP's
| W5DVMESDBQ001 |  |  | e5dr15u12.myl.com | DELL PowerEdge R740 | 70YR6J3 | Te1/0/13 | Te2/0/13 |  | 5D-DVPG-PC-SERIALIZATION-SER-1145 | 1145 | 10.6.178.32/27 | 10.6.178.33 | 10.6.178.43 - 10.6.178.53 |  |  | 1145 | 10 IP's
| W5DVPEXDBP001 | [8 empty] | 5D-DVPG-PC-RFID-SER-1148 | 1148 | 10.6.178.64/27 | 10.6.178.65 | 10.6.178.75 - 10.6.178.85 |  |  | 1148 | 10 IP's
| W5DVUHLMNDBP001 | [8 empty] | 5D-DVPG-PC-MES-SER-1158 | 1158 | 10.6.178.96/27 | 10.6.178.97 | 10.6.178.107 - 10.6.178.117 |  |  | 1111 | 10 IP's
[10 empty] | 5D-DVPG-PC-DH-SER-1125 | 1125 | 10.6.178.128/27 | 10.6.178.129 | 10.6.178.139 - 10.6.178.149 |  |  | 1125 | 10 IP's
[10 empty] | 5D-DVPG-PC-INFRA-SER-1117 | 1117 | 10.6.176.128/25 | 10.6.178.129 | 10.6.176.141- 190 |  |  | 1117 | 10 IP's
[10 empty] | 5D-DVPG-PC-BACKUP-SER-1147 | 1147 | 10.6.177.0/25 | 10.6.177.1 | 10.6.177.11 - 10.6.177.20 |  |  | 1147 | 10 IP's
No | Application Name | Application Type (INFRA, MFG or ENT) CURRENT STATUS | Vlan Name | Vlan ID | Server | Client
1 | 5D-dvPG-LabX-1149 | MFG | MFG-LAB-SER | 1149 | 9 |  |  |  |  | SL.NO | Switch | Switch Serial Number | Switch Port | Server Name | Required VLAN'S
2 | 5D-dvPG-Uhlmann Packaging System-1145 | MFG | MFG-SERIALIZATION-SER | 1145 | 5 |  |  |  |  | 1 | HUN-5DKOM-DIST1 | JAE24040E5W | Te1/1/29 | e5dr15u10.myl.com | switchport trunk allowed vlan 84,86,151-154 switchport mode trunk
3 | 5D-dvPG-RF ID-1148 | MFG | MFG-RFID-SER | 1148 | 2 |  |  |  |  | 2 | HUN-5DKOM-DIST2 | JAE23120NY0 | Te2/1/29
4 | 5D-dvPG-MES-MYMES-1111 | MFG | MFG-MES-SER | 1111 | 3 |  |  |  |  | 3 | HUN-5DKOM-DIST1 | JAE24040E5W | Te1/1/30 | e5dr15u12.myl.com
5 | 5D-dvPG-Data Historian-1125 | MFG | MFG-DH-SER | 1125 | 7 |  |  |  |  | 4 | HUN-5DKOM-DIST2 | JAE23120NY0 | Te2/1/30
6 | 5D-dvPG-Active Directory-1117 | MFG | MFG-INFRA-SER | 1117 | 7
7 | 5D-dvPG-Symantec Server-1117 | MFG | MFG-INFRA-SER | 1117 | 1
8 | 5D-dvPG-Backup Server-1147 | MFG | MFG-BACKUP-SER | 1147 | 2
9 | 5D-dvPG-Citrix Member-1117 | MFG | MFG-INFRA-SER | 1117 | 1
|  |  | Server name | NIC Ports | Speed
|  |  | e5drr15u18.myl.com | vmnic2 | 10 Gbit/s
|  |  |  | vmnic3 | 10 Gbit/s
|  |  | e5drr15u20.myl.com | vmnic2 | 10 Gbit/s
|  |  |  | vmnic3 | 10 Gbit/s
|  |  | e5dr15u10.myl.com | vmnic2 | 10 Gbit/s
|  |  |  | vmnic3 | 10 Gbit/s
|  |  | e5dr15u12.myl.com | vmnic2 | 10 Gbit/s
|  |  |  | vmnic3 | 10 Gbit/s
|  | Current Switch | Need To Connect On | Current Switch | Need To Connect On
| SL.NO | HUN-5DKOM-DIST1(JAE24040E5W)----> | HUN-5DKOM-MFG-DIST-SW1(FOC2431L517) | HUN-5DKOM-DIST1(JAE23120NY0)---> | HUN-5DKOM-MFG-DIST-SW1(FOC2431L50Y) | Server HostName | Make & Model | Server Serial Number | Remarks
| 1 | TenGigabitEthernet1/1/1 | Te1/0/3 | TenGigabitEthernet2/1/2 | Te2/0/4 | e5dr15u10.myl.com | DELL PowerEdge R740 | 80YR6J3 | Move the 10Gig SFP and fiber cable from the current switch to the mentioned switch.
| 2 | TenGigabitEthernet1/2/2 | Te1/0/13 | TenGigabitEthernet2/2/1 | Te2/0/13 | e5dr15u12.myl.com | DELL PowerEdge R740 | 70YR6J3 | Move the 10Gig SFP and fiber cable from the current switch to the mentioned switch.
DD Server MFG 10Gig Connections
172.18.80.24
root
Viatris123
|  | Source |  |  | Destination
|  | Switch Name | Switch serial number | Switch Port number | Server name | Server serial number | Server N/W Data ports
|  | HUN-5DKOM-MFG-DIST-SW1 | FOC2431L517 | Te1/1/8 | s5ddd003.myl.com | 3ZL6TY3 | NIC Slot 5 Port 3 |  | Vendor Name | CISCO-AVAGO
|  | HUN-5DKOM-MFG-DIST-SW1 | FOC2431L50Y | Te2/1/8 | s5ddd003.myl.com | 3ZL6TY3 | NIC Slot 7 Port 1 |  | Part Number | SFBR-709SMZ-CS1
[9 empty] | Serial Number | AVD212096EW
|  | Action Required: | [6 empty] | Revision | G4.1
|  | 1) Insert the 10Gig SFPs into both MFG DIST switches on the mentioned ports. | [6 empty] | Device Identifier | SFP/SFP+/SFP28
2) Insert the 10Gig SFPs into the server ports as mentioned above.
3) Connect the fiber cables at both the switch end and server end.
|  | 4) Monitor the LED status and confirm with us. | [6 empty] | Vendor Name | CISCO-ACCELINK
[9 empty] | Part Number | RTXM228-551-C88
[9 empty] | Serial Number | ACW282601YW
| Cluster | ENT servers | Remarks | N/W |  |  |  |  | Revision | 1
| 5DHADRS001 | W5DVPRINTP001 | Logged in | 5D-dvPG-ATM-Prod-152 |  |  |  |  | Device Identifier | SFP/SFP+/SFP28
| 5DHADRS002 | w5dfp001 | Rollback to 5DHADRS002 | DVPG-VMNetwork-86
| 5DHADRS002 | W5DSECP001 | Rollback to 5DHADRS002 | DVPG-VMNetwork-86
| 5DHADRS002 | w5dsec001 | Rollback to 5DHADRS002 | DVPG-VMNetwork-86
| 5DHADRS002 | w5dsccmdp001 | Rollback to 5DHADRS002 | DVPG-VMNetwork-86
| 5DHADRS002 | C5D19VCTXXEN001 | Yet to migrate | DVPG-VMNetwork-86
| 5DHADRS002 | C5D19VCTXXEN002 | Yet to migrate | DVPG-VMNetwork-86
| 5DHADRS002 | C5D19VCTXXEN003 | Yet to migrate | DVPG-VMNetwork-86
| Server Name | Cluster | IP Address-OLD | IP Address - NEW | Subnet | Gateway | AD - Primary | AD-Secondary
| W5DVFTOPCD001 | 5DHADRS002 | 10.248.200.11 | 10.6.178.131 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
| W5DVGDHFTIP001 | 5DHADRS002 | 10.248.201.9 | 10.6.178.132 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVGDHPINTP001 | 5DHADRS002 | 10.248.201.5 | 10.6.178.133 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVGDHPINTP002 | 5DHADRS002 | 10.248.201.4 | 10.6.178.134 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVGDINOPCD001 | 5DHADRS001 | 10.248.200.16 | 10.6.178.135 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVGDINPIOP001 | 5DHADRS002 | 10.248.201.23 | 10.6.178.151 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVGDINPIOP002 | 5DHADRS002 | 10.248.201.24 | 10.6.178.152 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVGDSHFDBP001 | 5DHADRS001 | 10.248.203.15 | 10.6.178.153 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVGDSHFTAP001 | 5DHADRS001 | 10.248.201.21 | 10.6.178.154 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVGDSHFTP001 | 5DHADRS002 | 10.248.201.19 | 10.6.178.155 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
| W5DVSDHRTRP001 | 5DHADRS001 | 10.248.201.6 | 10.6.178.156 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141
Migration Activity ON: 17-Apr-25
Sl.No | ServerName | IP Address-OLD | IP Address - NEW | Subnet | Gateway | AD - Primary | AD-Secondary | VLAN
1 | W5DVFTOPCD001 | 10.248.200.11 | 10.6.178.131 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19 | 1125
2 | W5DVGDHFTIP001 | 10.248.201.9 | 10.6.178.132 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
3 | W5DVGDHPINTP001 | 10.248.201.5 | 10.6.178.133 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
4 | W5DVGDHPINTP002 | 10.248.201.4 | 10.6.178.134 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
5 | W5DVGDINOPCD001 | 10.248.200.16 | 10.6.178.135 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
6 | W5DVGDINPIOP001 | 10.248.201.23 | 10.6.178.151 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
7 | W5DVGDINPIOP002 | 10.248.201.24 | 10.6.178.152 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
8 | W5DVGDSHFDBP001 | 10.248.203.15 | 10.6.178.153 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
9 | W5DVGDSHFTAP001 | 10.248.201.21 | 10.6.178.154 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
10 | W5DVGDSHFTP001 | 10.248.201.19 | 10.6.178.155 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
11 | W5DVSDHRTRP001 | 10.248.201.6 | 10.6.178.156 | 255.255.255.224 | 10.6.178.129 | 10.6.176.141 | 172.18.86.19
Migration Activity ON: 29-Apr-25
Sl.No | Hostname | Cluster | Migration to MFG 2.0 | Application | Target VRF | Target VLAN | IP Address - NEW | Subnet | Gateway | AD - Primary | AD-Secondary | Backup
1 | W5DVPEXAPPP001 | 5DHADRS003 | 2025-03-27 | PACKAGING | MFG-SERIALIZATION-SER | 1145 | 10.6.178.41 | 255.255.255.224 | 10.6.178.33 | 10.6.176.141 | 172.18.86.19 | 10.6.177.12
2 | W5DVPEXDBP001 | 5DHADRS003 | 2025-03-27 | PACKAGING | MFG-SERIALIZATION-SER | 1145 | 10.6.178.42 | 255.255.255.224 | 10.6.178.33 | 10.6.176.141 | 172.18.86.19 | 10.6.177.12
3 | W5DVUHLMNDBP001 | 5DHADRS003 | 2025-03-27 | PACKAGING | MFG-SERIALIZATION-SER | 1145 | 10.6.178.43 | 255.255.255.224 | 10.6.178.33 | 10.6.176.141 | 172.18.86.19 | 10.6.177.12
Migration Activity ON: 20-Apr-25-Sunday
Sl.No | Hostname | Cluster | IP Address-OLD |  | IP Address - NEW | Subnet | Gateway | AD - Primary | AD-Secondary | Target VLAN | Migration to MFG 2.0 | Application
1 | W5DVEIHP001 | 5DHADRS001 | 10.248.201.15 |  | 10.6.178.101 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19 | 1158 | 2025-04-20 | MES
2 | W5DVJBOSAPP001 | 5DHADRS002 | 10.248.201.11 |  | 10.6.178.102 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
3 | W5DVJBOSSP002 | 5DHADRS001 | 10.248.201.17 |  | 10.6.178.103 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
4 | W5DVMESDBP001 | 5DHADRS002 | 10.248.203.11, 10.248.203.25 | 10.248.203.25-w5dclusp001.myl.com | 10.6.178.104,10.6.178.124 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
5 | W5DVMESDBP002 | 5DHADRS002 | 10.248.203.12, 10.248.203.26 | Old IP 1-0.248.203.26-d5mesdbp.myl.com-New IP-10.6.178.125 | 10.6.178.105,10.6.178.125 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
6 | W5DVMESDBQ001 | 5DHADRS002 | 10.248.202.12 |  | 10.6.178.106 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
7 | W5DVMESEIHP002 | 5DHADRS003 | 10.248.201.22 |  | 10.6.178.118 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
8 | W5DVMESEIHQ001 | 5DHADRS002 | 10.248.200.14 |  | 10.6.178.119 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
9 | W5DVMESJBSOQ001 | 5DHADRS002 | 10.248.200.13 |  | 10.6.178.120 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
10 | W5DVSOSP001 | 5DHADRS001 | 10.248.201.20 |  | 10.6.178.121 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
11 | W5DVSOSP002 | 5DHADRS001 | 10.248.201.16 |  | 10.6.178.122 | 255.255.255.224 | 10.6.178.97 | 10.6.176.141 | 172.18.86.19
Build Vm's at 5D-KOM site DM: Shital N Parent RITM: RITM5350700
Sl.no | New VM Build Requirement-5D-KOMOROM | Transition RITM | Hostname | IP Address | Environment
1 | RITM5350925 | RITM5379817 | C5DVCTXDBP001 | 10.6.176.144 | DB Servers-5D-KOM |  |  |  | Host | Physical Ports |  |  | VLAN
2 | RITM5350927 | RITM5379818 | C5DVCTXDBP002 | 10.6.176.145 |  |  |  |  | e5dr15u30.myl.com | vmnic4 | Device ID | HUN-5DKOM-DIST1.myl.com | 86
CTX Servers
3 | RITM5350921 | RITM5391346 | C5DVCTXSTR001 | 10.6.176.148 | Citrix Prod Servers-5D-KOM | [5 empty] | IP address | 172.18.84.1
4 | RITM5350916 | RITM5391347 | C5DVCTXSTR002 | 10.6.176.149 | [6 empty] | Port ID | TenGigabitEthernet2/2/8
5 | RITM5350922 | RITM5389769 | C5DVCTXDDC001 | 10.6.176.154 | [6 empty] | Device ID | HUN-5DKOM-DIST1.myl.com
6 | RITM5350918 | RITM5389776 | C5DVCTXDDC002 | 10.6.176.151 |  |  |  |  | vmnic7 |  | IP address | 172.18.84.1
7 | RITM5350928 | RITM5389777 | C5DVCTXXEN001 | 10.6.176.152 | [6 empty] | Port ID | TenGigabitEthernet1/2/8
8 | RITM5350924 | RITM5389778 | C5DVCTXXEN002 | 10.6.176.153
CTX MES Servers
9 | RITM5350926 | RITM5389780 | C5DVCTXMES001 | 10.6.178.111
10 | RITM5350917 | RITM5391349 | C5DVCTXMES002 | 10.6.178.112 |  | W0BSCOMMGMTP004.myl.com | 172.20.86.245 |  | e5dr15u32.myl.com | vmnic4 | Device ID | HUN-5DKOM-DIST1.myl.com
11 | RITM5350923 | RITM5391350 | C5DVCTXMES003 | 10.6.178.113 |  | W0BSCOMMGMTP005.myl.com | 172.20.86.246 |  |  |  | IP address | 172.18.84.1
12 | RITM5350920 | RITM5391351 | C5DVCTXMES004 | 10.6.178.115 |  | W0BSCOMMGMTP006.myl.com | 172.20.86.247 |  |  | Port ID | TenGigabitEthernet2/1/24
[6 empty] | W0BSCOMMGMTP007.myl.com | 172.20.86.248 |  | vmnic7 | Device ID | HUN-5DKOM-DIST1.myl.com
[6 empty] | WB5SCOMGTYP001.myl.com | 10.250.84.72 |  |  | IP address | 172.18.84.1
[6 empty] | W6ESCOMGTYP002.myl.com | 172.25.146.24 |  |  | Port ID | TenGigabitEthernet1/1/24
MFG 2.o Citrix Infra Server ¦ 5D-HUNGARY ¦ RITM5350700
| Sl.No | Hostname | IP Address | Remarks
| 1 | C5DVCTXDBP001 | 10.6.176.144 | DB Servers
| 2 | C5DVCTXDBP002 | 10.6.176.145
| 3 | C5DVCTXSTR001 | 10.6.176.148 | Citrix Store Frontend Servers
| 4 | C5DVCTXSTR002 | 10.6.176.149
| 5 | C5DVCTXDDC001 | 10.6.176.154
| 6 | C5DVCTXDDC002 | 10.6.176.151
| 7 | C5DVCTXXEN001 | 10.6.176.152
| 8 | C5DVCTXXEN002 | 10.6.176.153
| 9 | C5DVCTXMES001 | 10.6.178.111 | Citrix MES Application Servers
| 10 | C5DVCTXMES002 | 10.6.178.112
| 11 | C5DVCTXMES003 | 10.6.178.113
| 12 | C5DVCTXMES004 | 10.6.178.115

## Sheet5
Name | Cluster | Guest OS | Memory Size | CPUs | IP Address-OLD | Application Details | Location | CI owner | Environment | Migration to MFG 2.0 | Application | Target VRF | Target VLAN | IP Address - NEW | Subnet | Gateway | AD - Primary | AD-Secondary | Backup
W5DVPEXAPPP001 | 5DHADRS003 | Microsoft Windows Server 2019 (64-bit) | 16 GB | 4 | 10.248.201.10 | Application Server for Uhlmann Pexcite PROD | Komarom | Csaba Szabo | PROD | 2025-03-27 | PACKAGING | MFG-SERIALIZATION-SER | 1145 | 10.6.178.41 | 255.255.255.224 | 10.6.178.33 | 10.6.176.141 | 172.18.86.19 | 10.6.177.12
W5DVPEXDBP001 | 5DHADRS003 | Microsoft Windows Server 2019 (64-bit) | 64 GB | 8 | 10.248.203.16 | Database Server for Uhlmann Pexcite PROD | Komarom | Csaba Szabo | PROD | 2025-03-27 | PACKAGING | MFG-SERIALIZATION-SER | 1145 | 10.6.178.42 | 255.255.255.224 | 10.6.178.33 | 10.6.176.141 | 172.18.86.19 | 10.6.177.12
W5DVUHLMNDBP001 | 5DHADRS003 | Microsoft Windows Server 2019 (64-bit) | 16 GB | 4 | 10.248.203.10 | Packaging Planning support Server | Komarom | Csaba Szabo | PROD | 2025-03-27 | PACKAGING | MFG-SERIALIZATION-SER | 1145 | 10.6.178.43 | 255.255.255.224 | 10.6.178.33 | 10.6.176.141 | 172.18.86.19 | 10.6.177.12

## Milan-3J
Server Rack Num | Server Name | IDRAC IP | Server IP Address | Serial Number | Model
3 | W3JSEC001_NEW | 10.243.146.7 | 10.243.146.8 | 1N4JPQ3 | DELL PowerEdge R740
4 | 3JDC01 | 172.18.190.62 | 172.18.190.19 | H0537Y3 | DELL PowerEdge R750
2 | w3jfp001-old | 172.18.190.117 | 172.18.190.23 | 2F6BHK3 | DELL PowerEdge R740
1 | w3jpsccmdp001 | 172.18.190.2 | 172.18.190.3 | HCHPV34 | PowerEdge R760

## E2-ISTMFG(Wb5)
Sl.No | Parent RITM/Intake ID | Title | State | Build Verification Task/CR Number/ATM Number | Transition RITM | Location | Hostname | IP Address | IDRAC Creds | ESXi Creds
1 | RITM5277511 | ESXi build at E2-ISTMFG | Build In Progress | CHG0182813 | RITM5350947 | E2-ISTMFG | ee2rr05u02 | 10.230.72.35 | root/$3CuredW@ll! | root/20Pme1esx!
2 |  | ESXi build at E2-ISTMFG | Build In Progress | CHG0182817 | RITM5350959 | E2-ISTMFG | ee2rr05u03 | 10.230.72.36
3 |  | ESXi build at E2-ISTMFG | Build In Progress | CHG0182819 | RITM5350960 | E2-ISTMFG | ee2rr05u04 | 10.230.72.37
4 |  | ESXi build at E2-ISTMFG | Build In Progress | CHG0182820 | RITM5350962 | E2-ISTMFG | ee2rr05u05 | 10.230.72.38
ee2rr05u02
| IDRAC --> 10.230.72.50 | [10 empty] | E2HADRS001 Esxi License
| Mgmt --> 10.230.72.35 | [6 empty] | NFS |  |  |  | QN0CL-AEL42-58LN8-018R4-28270
| vmotion --> 10.230.74.85 | E2-DVPG-PC-vMotion-2010 | Subnet mask | 255.255.255.192 |  |  |  | Subnet mask | 255.255.255.192
| NFS --> 10.230.73.150 | E2-DVPG-PC-NFS-2005 | Default gateway | 10.230.74.65 |  |  |  | Default gateway | 10.230.73.129
| ee2rr05u03 | [6 empty] | DNS server addresses | 10.230.72.75, 10.250.31.23
IDRAC --> 10.230.72.51
| Mgmt --> 10.230.72.36 |  |  | VM
| vmotion --> 10.230.74.86 |  |  | Vlan : 3078
NFS --> 10.230.73.151
| ee2rr05u04 |  |  | Vmotion
| IDRAC --> 10.230.72.52 |  |  | Vlan : 2010
Mgmt --> 10.230.72.37
| vmotion --> 10.230.74.87 |  |  | NFS |  |  |  |  | VMOTION: |  | NFS:
| NFS --> 10.230.73.152 |  |  | Vlan : 2005 |  |  |  |  | IPv4 address | 10.230.74.85 (static) | IPv4 address | 10.230.73.150 (static)
| ee2rr05u05 | [7 empty] | Subnet mask | 255.255.255.192 | Subnet mask | 255.255.255.192
| IDRAC --> 10.230.72.53 | [7 empty] | Default gateway | 10.230.74.65 | Default gateway | 10.230.73.129
| Mgmt --> 10.230.72.38 | [9 empty] | DNS server addresses | 10.230.72.7510.250.31.23
vmotion --> 10.230.74.88
NFS --> 10.230.73.153

## EXP
[5 empty] | *** | 17666*6 |  | Car EMI
Sl.No | Oct 2024 Expense | INR | Status | Remarks
1 | Ration | 3740 | Done |  | Sl.No | Jan 2025 Expense | INR | Status | Remarks
2 | House Rent | 12500 | Done | 4k cash remains | 1 | Ration | 3680 | Done | Done
3 | Car Loan | 17666 | Done |  | 2 | House Rent | 13417 | Done | Done
4 | Mutual Fund | 14000 | Done |  | 3 | Car Loan | 17666 | Done | Done
5 | Metro Recharge | 900 | Done |  | 4 | Mutual Fund | 17000 | Done | Done
6 | Credit card | 2500 | Done |  | 5 | Metro Recharge | 1000 | Done | Done
7 | Medicine | 1200 | Done |  | 6 | Moved to SBI |  | Done | Done
8 | Bglkt Expense on 9th Oct | 5500 | Done |  | 7 | Suzlon&TATA steel stocks | 12000 | Done | Done
9 | Moved to SBI | 20000 | Done |  | 8 | Gold Ring Confirmed | 5000 | Done | Done
10 | Scooty Petrol | 1000 |  |  | 9 | Medicine & scooty Petrols, car petrol | 2000 |  | Done
11 | Total | 75266 |  |  | 10 | Total
12 | Salary | 100301 |  |  | 11 | Balance
13 | Exp | 49766
14 | Balance | 50635 |  |  | Sl.No | Feb 2025 Expense | INR | Status | Remarks
[5 empty] | 1 | Ration | 3460 | Done
Sl.No | Nov 2024 Expense | INR | Status | Remarks | 2 | House Rent | 13417 | Done | 6500/- cash from Venkatesh
1 | Ration | 4500 | Done |  | 3 | Car Loan | 17666 | Done
2 | House Rent | 13500 | Done | 6300 cash given by venkatesh | 4 | Mutual Fund | 14000 | Done
3 | Car Loan | 17666 | Done |  | 5 | Metro Recharge | 1000
4 | Mutual Fund | 14000 | Done |  | 6 | Moved to SBI | 20500 | Done
5 | Metro Recharge | 1000 | Done |  | 7 | Suzlon&TATA steel stocks | 2000 | Done
6 | Bike Trip | 3000 | Done |  | 9 | Medicine & scooty Petrols, car petrol | 2000 | Done
7 | Moved to SBI | 30000 | Done |  | 10 | Total | 100301
8 | Scooty Petrol | 1000 | Done |  | 11 | Balance
9 | Total | 84666
10 | Balance | 100301 |  |  | Sl.No | Feb 2025 Expense | INR | Status | Remarks
[5 empty] | 1 | Ration | 3800 | Done
Sl.No | Dec 2024 Expense | INR | Status | Remarks | 2 | House Rent | 13368 | Done | 6500/- cash from Venkatesh
1 | Ration | 3000 | Done |  | 3 | Car Loan | 17666 | Done
2 | House Rent | 13384 | Done | 6500/- rcvd. | 4 | Mutual Fund | 14000 | Done
3 | Car Loan | 17666 | Done |  | 5 | Metro Recharge | 1400 | Done
4 | Mutual Fund | 14000+7000(Kuvera App) | Done |  | 6 | Given to Ramu | 10000 | Done
5 | Metro Recharge | 800 | Done |  | 7 | Moved to KBL | 5000 | Done
6 | Credit card Bill | 1500 | Done |  | 8 | LIC Payment | 6000 | Done
7 | Moved to SBI | 10000 | Done |  | 9 | Kite\KUVERA Saving | 6000 | Done
8 | Suzlon&TATA steel stocks | 5500 | Done |  | 10 | Medicine & scooty Petrols, car petrol | 2000 | Done
9 | Gold Ring Confirmed | 2000 | Done | 2k Advance Given=22k yet to pay | 11 | Total | 100301
10 | Wayanad Trip | 4800 | Done |  | 12 | Balance | 31500
11 | Medicine & scooty Petrols, car petrol | 4200
11 | Total | 62850 |  |  | Sl.No | Mar 2025 Expense | INR | Status | Remarks
12 | Balance | 13,400(HDFC), 95,702(SBI) |  |  | 1 | Ration | 2400 | Done
[5 empty] | 2 | House Rent | 13368 | Done | 6000/- cash from Venkatesh
[5 empty] | 3 | Car Loan | 17666 | Done
| Sl No | Date | Hours | NTT Portal | 4 | Mutual Fund | 14000 | Done
| 1 | 2025-05-09 | 12 |  | 5 | Metro Recharge | 1000 | Done
| 2 | 2025-05-10 | 4 |  | 6 | Given to Ramu | 5000 | Done
| 3 | 2025-05-13 | 12 |  | 7 | Moved to KBL & SBI | 10000 | Done
| 4 | 2025-05-15 | 11 |  | 9 | Kite\KUVERA Saving | 7000 | Done
| 5 | 2025-05-16 | 11 |  | 10 | Medicine & scooty Petrols, car petrol | 3200 | Done
| 6 | 2025-05-17 | 5 |  | 11 | Total
| 7 | 2025-05-18 | 4 |  | 12 | Balance
8
[5 empty] | Sl.No | Mar 2025 Expense | INR | Status | Remarks
[5 empty] | 1 | Ration | 3450 | Done
| April Exra hours worked | Total | 59 |  | 2 | House Rent | 13350 | Done | 6500/- cash from Venkatesh
| May Extra hours worket | Total | 23 |  | 3 | Car Loan | 17666 | Done
| Earned Leave | 9.66 |  |  | 4 | Mutual Fund | 14000 | Done
|  | Balance |  |  | 5 | Metro Recharge | 900 | Done
[5 empty] | 6 | Given to Ramu | 4000 | Done
|  | Full & Finan Settlement from VARITE on July 25th 2025 |  |  | 7 | Moved to KBL & SBI | 10000 | Done
|  | 16 Days Salary |  |  | 8 | Tailor Shop | 3800 | Done
|  | 23Hrs extra Salary |  |  | 9 | Kite\KUVERA Saving | 13000 | Done
|  | Earned Leave Salary |  |  | 10 | Medicine & scooty Petrols, car petrol |  |  |  | Sl No | Date | Hours
[5 empty] | 11 | Total |  |  |  | 1 | 2025-05-10 | 4Hr-Saturday
[5 empty] | 12 | Balance |  |  |  | 2 | 2025-05-17 | 5Hr-Saturday
[10 empty] | 3 | 2025-05-18 | 4Hr-Saturday
[5 empty] | Sl.No | Mar 2025 Expense | INR | Status | Remarks
[5 empty] | 1 | Ration | 2740 | Done
[5 empty] | 2 | House Rent | 13835 | Done | 6500/- cash from Venkatesh
[5 empty] | 3 | Car Loan | 17666 | Done
[5 empty] | 4 | Mutual Fund | 8000 | Done
[5 empty] | 5 | Moved to KBL & SBI | 4249 | Done
[5 empty] | 6 | Kite\KUVERA Saving | 10800 | Done
[5 empty] | 7 | Medicine & scooty Petrols, car petrol, Metro | 1100 | Done
[5 empty] | 8 | Total | 55650
[5 empty] | 9 | Balance | 110000
-54350

## Exp-25-Bri
Sl.No | Mar 2025 Expense | INR | Status | Remarks
1 | Ration | 3800 | Done
2 | House Rent | 13283 | Done | 6500/- cash from Venkatesh
3 | Car Loan | 17666 | Done
4 | Mutual Fund | 8000 | Done
5 | Moved to KBL & SBI
6 | Kite\KUVERA Saving
7 | Medicine & scooty Petrols, car petrol, Metro
8 | Total
9 | Balance

## Mylan to MFG or Partner or AWS
No. | Application Name | Source Description | Source IPs/Network | Ports/Protocols | Direction | Destination Description | Destination IPs/Network | Ports/Protocols | Purpose | Firewall Device | Requesting Mylan Business User | Requesting Mylan IT Contact
1 | API Node | Uhlmann Line server | 172.18.91.121 | 4840 | <--> | W5DVGDINOPCD001 | 10.248.200.16 | TCP | Port 4840 should be opend Bi-directional between the source system and destination server request to transfer and collect the data.
172.18.91.122
172.18.91.123
172.18.91.124
172.18.91.126
172.18.91.125
172.18.91.127
172.18.91.25
172.18.91.160
2 | API Node | Uhlmann Line server | 172.18.91.121 | 4840 | <--> | W5DVGDINPIOP001 | 10.248.201.23 (VLAN ID152) | TCP | Port 4840 should be opend Bi-directional between the source system and destination server request to transfer and collect the data.
172.18.91.122
172.18.91.123
172.18.91.124
172.18.91.126
172.18.91.125
172.18.91.127
172.18.91.25
172.18.91.160
3 | API Node | Uhlmann Line server | 172.18.91.121 | 4840 | <--> | W5DVGDINPIOP002 | 10.248.201.24 (VLAN ID152) | TCP | Port 4840 should be opend Bi-directional between the source system and destination server request to transfer and collect the data.
172.18.91.122
172.18.91.123
172.18.91.124
172.18.91.125
172.18.91.126
172.18.91.127
172.18.91.25
172.18.91.160
4 | PI API Node-Komaram(Dev) & | W5DVGDINOPCD001 | 10.248.200.16 | TCP 5450 | > | WA5CGDHAPPD005 | 10.104.19.244 | TCP 5450 | Port 5450 should be opened to communicate between PI API Node-Dev Komaram & GDH API Node Dev and PI DA Dev server
GDH API Node Dev
5 | GDH API Node(Dev)-Komaram | W5DVGDINOPCD001 | 10.248.200.16 | TCP 5450 | > | WD2CGDHAPPD005 | 10.105.2.73 | TCP 5450 | Port 5450 should be opened to communicate between GDH API Node Dev -Komaram and GDH PI DA Dev server
6 | PI API Node Primary | W5DVGDINPIOP001 | 10.248.201.23 | TCP 5450 | > | WA5CGDHAPPQ001 | 10.104.16.240 | TCP 5450 | Port 5450 should be opened to communicate between PI API Node Primary and PI Data Archive server QUA.
7 | PI API Node Secondary | W5DVGDINPIOP002 | 10.248.201.24 | TCP 5450 | > | WA5CGDHAPPQ001 | 10.104.16.240 | TCP 5450 | Port 5450 should be opened to communicate between PI API Node Secondary and PI Data Archive server QUA
8 | PI API Node Primary | W5DVGDINPIOP001 | 10.248.201.23 | TCP 5450 | > | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5450 | Port 5450 should be opened to communicate between PI API Node Primary and PI Data Archive Primary server PRD
9 | PI API Node Secondary | W5DVGDINPIOP002 | 10.248.201.24 | TCP 5450 | > | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5450 | Port 5450 should be opened to communicate between PI API Node Secondary and PI Data Archive Primary server PRD
10 | PI Asset Framework | W5DVGDSHFTAP001 | 10.248.201.21 | TCP 5450 | > | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5450 | Port 5450 should be opened to communicate between PI Asset Framework server and PI Data Archive Primary server
11 | PI Clients | W5DVGDHFTIP001 | 10.248.201.9 | TCP 5450 | > | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5450 | Port 5450 should be opened to communicate between PI Data Archive Primary server and PI Clients server
12 | GDH PI Vision | W6EVGDHPIVIP001 | 10.248.177.104 | TCP 5450 | > | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5450 | Port 5450 should be opened to communicate between PI Data Archive Primary server and GDH PI Vision PRD server
13 | GDH RtReports | W6EVGDHRTRP001 | 10.248.177.105 | TCP 5450 | > | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5450 | Port 5450 should be opened to communicate between PI Data Archive Primary server and GDH RtReports PRD server
14 | PI Data Archive Primary | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5457 | > | W5DVGDSHFTAP001 | 10.248.201.21 | TCP 5457 | Port 5457 should be opened to communicate between PI Data Archive Primary server and PI Asset Framework server
15 | SQL Server | W5DVGDSHFDBP001 | 10.248.203.15 | TCP 5457 | > | W5DVGDSHFTAP001 | 10.248.201.21 | TCP 5457 | Port 5457 should be opened to communicate between MSSQL DB server and PI Asset Framework server
16 | PI Clients | W5DVGDHFTIP001 | 10.248.201.9 | TCP 5457 | > | W5DVGDSHFTAP001 | 10.248.201.21 | TCP 5457 | Port 5457 should be opened to communicate between PI Clients server and PI Asset Framework server
17 | GDH PI Vision | W6EVGDHPIVIP001 | 10.248.177.104 | TCP 5457 | > | W5DVGDSHFTAP001 | 10.248.201.21 | TCP 5457 | Port 5457 should be opened to communicate between GDH PI Vision PRD server and PI Asset Framework server
18 | GDH RtReports | W6EVGDHRTRP001 | 10.248.177.105 | TCP 5457 | > | W5DVGDSHFTAP001 | 10.248.201.21 | TCP 5457 | Port 5457 should be opened to communicate between GDH RtReports PRD server and Asset Framework server
19 | PI Asset Framework | W5DVGDSHFTAP001 | 10.248.201.21 | TCP 1433 | > | W5DVGDSHFDBP001 | 10.248.203.15 | TCP 1433 | Port 1433 should be opened to communicate between PI Asset Framework server and MSSQL DB server
20 | PI Asset Framework | W5DVGDSHFTAP001 | 10.248.201.21 | TCP 25 | > | hub.myl.com | hub.myl.com | TCP 25 | Port 25 should be opened as application will send notifications to the end users
21 | PI Clients | W5DVGDHFTIP001 | 10.248.201.9 | TCP 443 | > | W6EVGDHPIARP001 | 10.248.177.102 | TCP 443 | Port 443 should be opened to communicate between PI Client server and GDH PI Data Archive PRD server
22 | GDH RtReports | W6EVGDHRTRP001 | 10.248.177.105 | TCP 443 | > | W5DVGDHFTIP001 | 10.248.201.9 | TCP 443 | Port 443 should be opened to communicate between GDH RtReports PRD server and PI Clients server
23 | GDH API Node Primary | W5DVGDHPINTP001 | 10.248.201.5 | TCP 5450 | > | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5450 | Port 5450 should be opened to communicate between GDH PI API Node Primary PRD and PI Data Archive Primary server PRD
24 | GDH API Node Secondary | W5DVGDHPINTP002 | 10.248.201.4 | TCP 5450 | > | W5DVGDSHFTP001 | 10.248.201.19 | TCP 5450 | Port 5450 should be opened to communicate between GDH PI API Node Secondary PRD and PI Data Archive Primary server PRD
25 | GDH API Node Primary | W5DVGDHPINTP001 | 10.248.201.5 | TCP 5450 | > | W6EVGDHPIARP001 | 10.248.177.102 | TCP 5450 | Port 5450 should be opened to communicate between GDH PI API Node Primary PRD and GDH PI Data Archive server PRD
26 | GDH API Node Secondary | W5DVGDHPINTP002 | 10.248.201.4 | TCP 5450 | > | W6EVGDHPIARP001 | 10.248.177.102 | TCP 5450 | Port 5450 should be opened to communicate between GDH PI API Node Secondary PRD and GDH PI Data Archive server PRD
27 | GDH API Node Primary | W5DVGDHPINTP001 | 10.248.201.5 | TCP 5450 | > | W6EVGDHPIARQ001 | 10.248.176.103 | TCP 5450 | Port 5450 should be opened to communicate between GDH PI API Node Primary PRD and GDH PI Data Archive server QUA
28 | GDH API Node Secondary | W5DVGDHPINTP002 | 10.248.201.4 | TCP 5450 | > | W6EVGDHPIARQ001 | 10.248.176.103 | TCP 5450 | Port 5450 should be opened to communicate between GDH PI API Node Secondary PRD and GDH PI Data Archive server QUA